## Release Burndown
| Start Date for First Sprint of Release | 2007-08-10
| Days per Sprint: | 14
| Number of Sprints in Release: | 16
| Total Story Points Remaining: | 86 | 86
Sprint Ending Dates
ID | Story Title | 2007-08-10 | 2007-08-24 | 2007-09-07 | 2007-09-21 | 2007-10-05 | 2007-10-19 | 2007-11-02 | 2007-11-16 | 2007-11-30 | 2007-12-14 | 2007-12-28 | 2008-01-11 | 2008-01-25 | 2008-02-08 | 2008-02-22 | 2008-03-07 | 2008-03-21
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Story Points Remaining
1 | Story 1 | 2007-08-10: 5; 2007-08-24: 5
2 | Story 2 | 2007-08-10: 3; 2007-08-24: 3
3 | Story 3 | 2007-08-10: 8; 2007-08-24: 8
4 | Story 4 | 2007-08-10: 8; 2007-08-24: 8
5 | Story 5 | 2007-08-10: 12; 2007-08-24: 12
6 | Story 6 | 2007-08-10: 13; 2007-08-24: 13
7 | Story 7 | 2007-08-10: 21; 2007-08-24: 21
8 | Story 8 | 2007-08-10: 8; 2007-08-24: 8
9 | Story 9 | 2007-08-10: 8; 2007-08-24: 8
Insert New Rows Above this Line
| Projected Burndown Increment (each Sprint) | 2007-08-10: 5.375
| Projected Target Track | 86 | 80.625 | 75.25 | 69.875 | 64.5 | 59.125 | 53.75 | 48.375 | 43 | 37.625 | 32.25 | 26.875 | 21.5 | 16.125 | 10.75 | 5.375 | 0

## Chart
`

## Instructions
1) List all stories in the release. In column "D", enter size points for each story.
2) At end of sprint:
2.1 | For all the stories listed, copy the points remaining into the next column.
2.2 | Zero out remaining points for any stories that were completed during the sprint.
2.3 | Copy the summation column (row 8, "Total Story Points Remaining") into the next column.