## Release Calculator
Release Buffer Points
| Sum | 210 | 399 | 189 | 3165 | > sqrt > | 56.2583 |  | 126.8%
|  | 210 |  |  |  | + | 56.2583 | = | 266.2583
[8 empty] | Expected Velocity Points | Sprints Needed | Sprint Days
[8 empty] | 20 | 13 | 14
(1, 2, 3, 5, 8, 13, 21, 34, 55)
[7 empty] | Start/End Dates: | 2007-10-14 | 2008-04-13
"x" to Include | Story ID | 50/50 Points | 90/10 Points | Local Safety | Local Safety Squared | Estimated Sprint | Estimated End of Sprint Date
x | S-1 | 1 | 2 | 1 | 1 | 1 | 2007-10-28 | 1.2679 | 1.2679
x | S-2 | 2 | 3 | 1 | 1 | 1 | 2007-10-28 | 2.5358 | 3.8037
x |  | 5 | 5 | 0 | 0 | 1 | 2007-10-28 | 6.3395 | 10.1432
x |  | 5 | 8 | 3 | 9 | 1 | 2007-10-28 | 6.3395 | 16.4827
x |  | 8 | 13 | 5 | 25 | 1.3313 | 2007-10-28 | 10.1432 | 26.6258
x |  | 13 | 21 | 8 | 64 | 2.1554 | 2007-11-11 | 16.4827 | 43.1085
x |  | 21 | 34 | 13 | 169 | 3.4867 | 2007-11-25 | 26.6258 | 69.7343
x |  | 34 | 55 | 21 | 441 | 5.6421 | 2008-01-06 | 43.1085 | 112.8428
x |  | 55 | 89 | 34 | 1156 | 9.1289 | 2008-02-17 | 69.7343 | 182.5771
x |  | 1 | 3 | 2 | 4 | 9.1923 | 2008-02-17 | 1.2679 | 183.845
x |  | 2 | 5 | 3 | 9 | 9.319 | 2008-02-17 | 2.5358 | 186.3808
x |  | 3 | 8 | 5 | 25 | 9.5092 | 2008-03-02 | 3.8037 | 190.1845
x |  | 5 | 8 | 3 | 9 | 9.8262 | 2008-03-02 | 6.3395 | 196.524
x |  | 21 | 34 | 13 | 169 | 11.1575 | 2008-03-16 | 26.6258 | 223.1498
x |  | 1 | 3 | 2 | 4 | 11.2209 | 2008-03-16 | 1.2679 | 224.4177
x |  | 2 | 5 | 3 | 9 | 11.3477 | 2008-03-16 | 2.5358 | 226.9535
x |  | 3 | 8 | 5 | 25 | 11.5379 | 2008-03-30 | 3.8037 | 230.7572
x |  | 5 | 21 | 16 | 256 | 11.8548 | 2008-03-30 | 6.3395 | 237.0967
x |  | 8 | 34 | 26 | 676 | 12.362 | 2008-03-30 | 10.1432 | 247.2399
x |  | 1 | 3 | 2 | 4 | 12.4254 | 2008-03-30 | 1.2679 | 248.5078
x |  | 2 | 5 | 3 | 9 | 12.5522 | 2008-04-13 | 2.5358 | 251.0436
x |  | 3 | 8 | 5 | 25 | 12.7424 | 2008-04-13 | 3.8037 | 254.8473
x |  | 3 | 8 | 5 | 25 | 12.9325 | 2008-04-13 | 3.8037 | 258.651
x |  | 3 | 8 | 5 | 25 | 13.1227 | 2008-04-13 | 3.8037 | 262.4546
x |  | 3 | 8 | 5 | 25 | 13.3129 | 2008-04-13 | 3.8037 | 266.2583
|  | 13 | 21 | 8 | 64 |  |  | 0 | 266.2583
|  | 13 | 21 | 8 | 64 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
|  |  |  | 0 | 0 |  |  | 0 | 266.2583
Insert above this line
Formulas:
Sprints Needed = [Expected Velocity Points]+(J7*K7)

## Instructions
The release calculator is used to estimate the completion date for a release.
It also estimates sprint boundaries; that is, which stories are likely to be worked on within specific sprints.
The calculator is capable of computing buffer time for the estimates using the standard formula: square root of the sum of the squares of local safety.
This mechanism is effective for quantifying "uncertainty" within the plan. The buffer is taken into account when estimating the end date and the sprint boundaries.
Instructions:
1) Add stories into the list in order of prioritization. (Use a unique identifier to map stories back to the product backlog.)
2) Add sizing points to each story. Uncertainty about the difficulty of a story is accounted for by using different values for 50/50 vs. 90/10.
50/50 = 50% certainty; expecting a "miss" will happen half of the time.
An optimistic estimate for the "smooth sailing" scenario.
90/10 = 90% certainty; trying to ensure an overrun will happen less than 10% of the time.
A pessimistic estimate for the "rough seas" scenario.
3) Set the average sprint-velocity estimate in points.
4) Set the date that the first sprint will begin.
5) Set the number of days for a sprint.
6) Stories can be included or excluded from the plan by placing or removing an "x" in the first column of the story row.