## Sprint Burndown
| Sprint Start Date: |  | 2007-08-10 |  | Daily Estimated Remaining
ID | Story/Task Title | Type | Status | Owner | 2007-08-10 | 2007-08-11 | 2007-08-12 | 2007-08-13 | 2007-08-14 | 2007-08-15 | 2007-08-16 | 2007-08-17 | 2007-08-18 | 2007-08-19 | 2007-08-20 | 2007-08-21 | 2007-08-22 | 2007-08-23
1.1 | As a tourist, I can search the product catalog for tours by a combination of tour type and location and view the results. - Example: Find all the boat tours from Anchorage. |  |  |  | 140 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1-01 | Develop search and results page wireframes | UI | In Progress | DRB | 16 | 16
1.1-02 | Design meeting | DEV | Completed | All | 8 | 8
1.1-03 | Implement search and results page HTML | DEV | In Progress |  | 24 | 24
1.1-04 | Implement controller | DEV | Not Started |  | 12 | 12
1.1-05 | Implement service methods | DEV | Completed | MJF | 16 | 16
1.1-06 | Add indexes to database schema | DB | Blocked |  | 8 | 8
1.1-07 | Create test plan and test cases | QA | In Progress | SR | 16 | 16
1.1-08 | Run tests | QA | Not Started |  | 24 | 24
1.1-09 | Test and fix time | DEV | Not Started |  | 16 | 16
2.1 | Description for some other story goes here. |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 1 | DOC | Not Started
| Task 2 | DOC | Not Started
| Task 3 | DOC | Not Started
| Task 4 | DOC | Not Started
| Task 5 | DOC | Not Started
| Task 6 | DOC | Not Started
| Task 7 | DOC | Not Started
| Task 8 | DOC | Not Started
| Task 9 | DOC | Not Started
3.1 | Description for some other story goes here. |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 1 | DOC | Not Started
| Task 2 | DOC | Not Started
| Task 3 | DOC | Not Started
| Task 4 | DOC | Not Started
| Task 5 | DOC | Not Started
| Task 6 | DOC | Not Started
| Task 7 | DOC | Not Started
| Task 8 | DOC | Not Started
| Task 9 | DOC | Not Started
4.1 | Description for some other story goes here. |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 1 | DOC | Not Started
| Task 2 | DOC | Not Started
| Task 3 | DOC | Not Started
| Task 4 | DOC | Not Started
| Task 5 | DOC | Not Started
| Task 6 | DOC | Not Started
| Task 7 | DOC | Not Started
| Task 8 | DOC | Not Started
| Task 9 | DOC | Not Started
5.1 | Description for some other story goes here. |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 1 | DOC | Not Started
| Task 2 | DOC | Not Started
| Task 3 | DOC | Not Started
| Task 4 | DOC | Not Started
| Task 5 | DOC | Not Started
| Task 6 | DOC | Not Started
| Task 7 | DOC | Not Started
| Task 8 | DOC | Not Started
| Task 9 | DOC | Not Started
| Total Estimated Remaining |  |  |  | 140 | 140
| Workdays | 8 |  |  | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1
| Projected Burndown Increment (each workday) | 17.5
| Projected Burndown Track |  |  |  | 140 | 140 | 140 | 122.5 | 105 | 105 | 87.5 | 70 | 70 | 70 | 52.5 | 35 | 17.5 | 0
| Data Validation Lists | UI | In Progress
|  | DEV | Completed
|  | DB | Not Started
|  | QA | Blocked
DOC

## Chart
`

## Holidays
List any non-working holidays in the range below.
Holidays
2007-01-01
2007-08-15
2008-01-01

## Instructions
Each day requires the copy/paste of an of a cell on the "Total Estimated Remaining" row.